## Sheet1
DATE | DAILY ROUTINE | DOCUMENT | TECHNICAL
2019-02-12 | Gone through the basics concepts of OOPS,SERVLET,AND BOOTSTRAP | Title was choosen
2019-03-12 | Abstract,gitup account is created,feasibility study was initiated,discussed with mam and venkat sir,proxy was checked | abstract for the main project "AUTOMATIC RESUME CORRECTION"was done.
2019-04-12 | Feasiblity study of the project "AUTOMATIC RESUME CORRECTION" was completed | Feasibility study for the main project "AUTOMATIC RESUME CORRECTION"was done.
2019-05-12 | Prepared for placement(quantitative,reasoning and verbal aptitude)
2019-09-12 | modules were added,prototype for the project was drawn | modules were designed.
2019-10-12 | register,login page were designed. The overall website and flow of it was drawn. | web pages drawn related to the project.
2019-11-12 | login and home page were designed.
12/12/2019 Data flow,front screens for admin ,faculty | dataflow,front screens for modules were drwan. | dataflow diagram for the project was drawn